## GTM
well | area | lu | sloy | well_pad | brigade | gtm_type | planned_work | start_date | end_date | duration_days | increment | liquid_increment | gas_increment | gor_change
WA_101 | Area East | LU_A | SLOY_A1 | PAD_A01 | KRS-01 | well_service | OPZ | 2026-06-15 | 2026-06-22 | 8 | 14 | 24 | 900 | 4
WA_201 | Area East | LU_A | SLOY_A2 | PAD_A02 | KRS-02 | fracturing | GRP | 2026-07-10 | 2026-07-19 | 10 | 18 | 30 | 1200 | 6
WA_401 | Area East | LU_A | SLOY_A1 | PAD_A03 | KRS-03 | new_well | NEW_WELL_START | 2026-08-01 | 2026-08-12 | 12 | 70 | 120 | 10800 | 90
WB_402 | Area West | LU_B | SLOY_B1 | PAD_B02 | KRS-04 | new_well | NEW_WELL_START | 2026-09-10 | 2026-09-22 | 13 | 78 | 135 | 12825 | 95
WB_301 | Area West | LU_B | SLOY_B1 | PAD_B01 | KRS-05 | rir | RIR | 2027-02-20 | 2027-03-03 | 12 | 16 | 28 | 1100 | 5
WA_101 | Area East | LU_A | SLOY_A1 | PAD_A01 | KRS-01 | well_service | OPZ_REPEAT | 2027-05-05 | 2027-05-11 | 7 | 10 | 18 | 600 | 2